## Title Page
Title Page
Date | 20-11-2022
Assignment Title
Group no.
Group members (Name, ID#) | Reema Rahman:160023214

## Total budgeted cost
Fast Food Startup Project | A | B | C
| Time Estimate(days) | Daily rate | A*B | Non-Labour Costs |  | C+D+E
2.0 Blueprint & architecture |  | Cdn $(1) & (2) | Labour costs | Equipment | Materials Required | Total
2.1 Blueprint Design and Architecture | 5 | 15000 | 75000 | 5000 | 10000 | 90000
2.2 Permits | 8 | 10000 | 80000 | 0 | 0 | 80000
2.3 Architecture Revised Drawings | 6 | 30000 | 180000 | 0 | 5000 | 185000
Subtotal | [5 empty] | 355000
3.0 New Menu
3.1 New Creations | 6 | 50000 | 300000 | 0 | 150000 | 450000
3.2 Food Presentation | 3 | 20000 | 60000 | 0 | 0 | 60000
3.3 Final food testing | 1 | 15000 | 15000 | 0 | 0 | 15000
3.4 Menu selection and design | 3 | 10000 | 30000 | 1500 | 0 | 31500
Subtotal | [5 empty] | 556500
4.0 Seating And Arrangement
4.1 Consumer behavioural studies | 4 | 10000 | 40000 | 8000 | 0 | 48000
4.2 Streamline foot traffic flow | 2 | 15000 | 30000 | 5000 |  | 35000
4.3 Furniture Design and selection | 7 | 25000 | 175000 | 0 | 0 | 175000
Subtotal | [5 empty] | 258000
5.0 Launch
5.1 Rollout soft launch | 2 | 50000 | 100000 | 150000 | 50000 | 300000
5.2 Testing | 5 | 35000 | 175000 | 0 | 150000 | 325000
5.3 Feedback from customers | 1 | 25000 | 25000 | 20000 |  | 45000
5.4 Employee training | 2 | 25000 | 50000 | 0 | 35000 | 85000
Subtotal | [5 empty] | 755000
6.0 Project Management and control
6.1 Project Charter | 2 | 25000 | 50000 | 20000 | 0 | 70000
6.2 Project Team development | 2 | 25000 | 50000 | 0 | 0 | 50000
6.3 Scope defination | 1 | 25000 | 25000 | 0 | 0 | 25000
6.4 project Schedule | 1 | 25000 | 25000 | 0 | 0 | 25000
6.5 project Budget | 1 | 25000 | 25000 | 0 | 0 | 25000
6.6 Risk/issue Management | 3 | 25000 | 75000 |  |  | 75000
6.7 Stakeholder and Communication Management | 4 | 25000 | 100000 |  | 2000 | 102000
6.8 Project Closure | [5 empty] | 0
Subtotal | [5 empty] | 372000
Total Effort | 69 |  |  |  |  | 2296500
Contigency on Labour | 500000
Total project budget | 2796500

## Time phased budget
| Time Estimate(days) | Plan on when the work will be done | [6 empty] | Per week Labour Cost | [6 empty] | Per Week Non Labour Costs | [6 empty] | Per Week Contingency Allocation | [6 empty] | Per Week Total Cost
2.0 Blueprint & architecture |  | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7
2.1 Blueprint Design and Architecture | 5 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 15000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 30000 | 30000 | 0 | 0 | 0 | 0
2.2 Permits | 8 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 20000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 30000 | 30000 | 0 | 0 | 0 | 0
2.3 Architecture Revised Drawings | 6 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 60000 | 60000 | 60000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 60000 | 60000 | 0 | 0
3.0 New Menu | [29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 New Creations | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 150000 | 150000 | 0 | 0 | 0 | 0
3.2 Food Presentation | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 20000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 40000 | 0 | 0 | 0
3.3 Final food testing | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0
3.4 Menu selection and design | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 10000 | 10000 | 0 | 0
4.0 Seating And Arrangement | [29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 Consumer behavioural studies | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 118000 | 10000 | 10000 | 10000 | 0 | 0 | 0
4.2 Streamline foot traffic flow | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 15000 | 0 | 0 | 0
4.3 Furniture Design and selection | 7 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 75000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 50000 | 50000 | 0 | 0 | 0
5.0 Launch | [29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 Rollout soft launch | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 300000 | 0 | 0
5.2 Testing | 5 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 105000 | 70000 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 145000 | 0
5.3 Feedback from customers | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0
5.4 Employee training | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 25000 | 0 | 0
6.0 Project Management and control | [29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 Project Charter | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0
6.2 Project Team development | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0
6.3 Scope defination | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0
6.4 project Schedule | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0
6.5 project Budget | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0
6.6 Risk/issue Management | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 0 | 0
6.7 Stakeholder and Communication Management | 4 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 25000 | 25000 | 25000
6.8 Project Closure | 0 | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort | 69 | [28 empty] | 613000 | 370000 | 436500 | 497000 | 640000 | 215000 | 25000
Total Cost | 2796500